## Estimated LOE
No. | Epic | User Story | Average Importance (out of 7) | Average Dysfunctional Score (out of 5) | Client Priority | Dev Size | Dev Complexity | Story Points | Sprint | UI/Front End LOE (hrs) | Back-end App LOE (hrs) | DB LOE (hrs) | Testing LOE
2 | Input Data | As a SSO user, I want to be able to enter my component's inventory and other data for the most recent quarter in a form so that I don't have to fill out an excel spreadsheet. | 0 | 0 | #N/A | Small | Low | 1 | S1 | 2 |  | 8 | 3
3 | Input Data | As a SSO user, I want to [some data fields?] to be prepopulated based on last quarter information for my component so that I can save time and only update what I need updating | 5 | 4 | Could | Small | Low | 1 | S1 | 3 |  | 4 | 1
4 | Input Data | As a SSO user, I want the system to check my data for accuracy and completeness so that I can immediately correct any mistakes before marking it for review. | 7 | 3 | Could | Small | Medium | 2 | S1 | 4 |  | 4 | 2
5 | Input Data | As a SSO user, I want to be able to save in-progress data so that I can edit and complete the data center quarterly information another time. | 7 | 2 | Question | Small | Medium | 2 | S1 | 3 |  | 8 | 0.5
6 | Input Data | As a SSO user, I want the system to highlight the fields that have been updated so that I (and others) know which field has new data. | 6 | 3 | Could | Medium | High | 5 | S1 | 6 |  | 8 | 0.5
7 | Input Data | As a SSO user/lead, I want the system to show me the delta between past quarter and current quarter data so that I am aware of the change. | 7 | 4 | Should | Small | Low | 1 | S1 | 1 |  | 8 | 1
9 | Start Quarter | As a GSA IT officer, I want to be able to start a new quarter so that I can begin the data gathering process for the quarter. | 6 | 4 | Should | Small | Low | 1 | S1 | 3 |  | 4 | 1
10 | Start Quarter | As a GSA IT officer, I want to be able to set an due date for the quarter inventory report so that I can receive the reports in a timely manner. | 6 | 4 | Should | Small | Low | 1 | S1 | 1 |  | 4 | 0
11 | Edit data | As a GSA IT officer, I want to be able to edit the latest quarter information for a data center so that I can update or correct data as needed. | 5 | 4 | Could | Medium | Medium | 3 | S1 | 5 |  | 8 | 1
12 | Edit data | As a GSA IT officer, I want to add notes to the latest quarter form for a data center so that I capture notable information for that quarter. | 7 | 5 | Must | Small | Low | 1 | S1 | 2 |  | 4 | 0.5
13 | Edit data | As a GSA IT officer, I want the system to detect and notify me of errors at the field level (based on Data Point's validations) on the form upon saving so that I can correct them earlier. | 6 | 5 | Must | Small | Medium | 2 | S1 | 3 |  | 0 | 1.5
14 | Edit data | As a GSA IT officer, I want to flag a form that has been validated by me so that I can push it for final review and validation. | 7 | 5 | Must | Small | Low | 1 | S1 | 1 |  | 4 | 1
21 | View Past Quarter data | As a GSA IT officer, I want to view data center reports from past quarters so that I can refer to past reports as needed. | 6 | 5 | Must | Small | Low | 1 | S1 | 2 |  | 16 | 1
22 | View Past Quarter data | As a GSA IT officer, I want all past reports organized by year, then quarter, then regions so that it is easier for me to find past reports. | 7 | 5 | Must | Medium | Medium | 3 | S1 | 4 |  | 0 | 0
23 | Search | As a GSA IT officer, I want to be able to search for data using Data Center ID/Name anywhere I am on the application so that I can quickly find the data center/report I want. | 6 | 5 | Must | Small | Medium | 2 | S1 | 5 |  | 0 | 1.5
28 | Capture Audit Trail | As an admin, I want the system to track changes made by any user at a field level so that I have an audit trail for each data center report/form. | 7 | 5 | Must | Large | High | 8 | S1 | 7 |  | 16 | 2
29 | Capture Audit Trail | As an admin, I want the system to track changes made by any user to a data center so that I have an audit trail for each data center. | 7 | 5 | Must | Large | Medium | 5 | S1 | 6 |  | 0 | 1

## Capacity
SPRINT 1
| Name | Planned Capacity | Group | Est. LOE (0.8 * Planned Cap) | Allocated LOE | % Diff
| Matt | 60 | Front-End App | 48 | 58 | 3.571% | Est.Loe = taking 20% of total planned cap. As buffer
| Sai | 10 |  | 8 |  |  | If % Difference is greater than 20%, highlight in RED
| Sara | 20 | UI | 16 | 0 | -100%
| Justin | 44 |  | 35.2
| Divakar | 10 | DB | 8 | 96 | 421.7%
| Adam | 13 |  | 10.4
| Stephanie | 30 | Back-End App | 24 | 0 | -100%
| Khanh | 20 | Testing | 16 | 18.5 | -27.73%
| Nick | 12 |  | 9.6